## Slide 1: Managing project and Teams
Lecture 4: Project Proposal

## Slide 2: ?
"If our project were a journey, and each team member a unique traveler, what mode of transportation would you choose to symbolize your role and why?"
Notes: Key aspects of architectural design e.g System components, Data management, Interfaces (User Interfaces and API’s), Architectural Styles ,Quality Attributes, Technology Selection

## Slide 3: Retrospection
Identify and describe project types and nature
Different project approaches
Request for Proposal
Project Lifecycle
Project Strategies
Notes: Key aspects of architectural design e.g System components, Data management, Interfaces (User Interfaces and API’s), Architectural Styles ,Quality Attributes, Technology Selection

## Slide 4: Key topics covered in this lecture

## Slide 5: What we will cover in this lecture
Recognize the purpose and importance of a project proposal in the project management process.
Identify and describe the key components of a project proposal, including the project scope, objectives, deliverables, timeline, and budget.
Types of contracts between the customer and the contractor
Measuring the success of proposal efforts
Notes: After studying this chapter, students should know how to:
Develop relationships with customers and partners
Decide whether to prepare a proposal in response to a customer’s RFP
Create a credible proposal
Determine a fair and reasonable price for a proposal
Discuss how customers evaluate proposals
Explain types of contracts and various terms and conditions
Measure the success of proposal efforts

## Slide 6: Building Relationships with Customers and Partners
Foundation for successful funding and opportunities
Requires good listening and constant learning
Frequent and regular contact; express appreciation for the client’s time
Trust is key and ethics are imperative
First impression is important
Problem solving and credibility grows with good performance
Partner with several key individuals in an organization
Notes: Building Relationships with Customers and Partners
Generally speaking, customers (clients) and partner organizations prefer to work with people they know and trust.
Relationships establish the foundation for successful funding and contract opportunities.
Relationship building requires being proactive and engaged.
It requires face-to-face contacts; it cannot be done as effectively through e-mail or phone conversations.
Relationship building requires being a good listener and a good learner. When you are with clients, ask questions and listen. Make the client feel good. Empathize with their issues, whether they are business or personal.
Contacts with potential clients should be frequent and regular– not just when there is a current opportunity for funding or just before they will be issuing a RFP. During contacts, do not focus on discussing potential contract opportunities.
  After meeting with a client, always express your appreciation and thank them for making the time to meet with you.
Establishing and building trust is key to developing effective and successful relationships with clients and partners. One way to foster this is to be reliable and responsive.
Ethical behavior in dealing with clients and partners is also imperative for building trust.
The first impression you make on a client is pivotal to developing a continuing and fruitful relationship.
Clients want to work with people who can solve problems, not with those who merely identify them.
Build credibility based on good performance.
Always put the client first. Clients want to be confident that any projects they undertake with the contractor will be successful, will involve a good working relationship with the contractor, and will help the clients achieve their business goals.
It is advisable not to rely on a good relationship with just one individual in a client or partner organization, but rather to build relationships with several key people in a client or partner organization, since key individuals may leave the organization while others become more influential.

## Slide 7: Common Principles for Project Initiation
Project initiation begins with divergent thinking to expand our understanding of the project before agreeing on a solution.
Project proposals are typically written during the initiation phase of the project lifecycle.
Notes: Understand the stakeholders. context of the issue through the eyes of all Invest in creativity.
Initiation presents the greatest opportunity to approach the issue with fresh, original ideas.
Be methodical in evaluating the options and testing assumptions.
Risk identiﬁcation in this phase pays huge dividends.
Involve a wide variety of stakeholders.
Quantify the benefits and costs of the alternatives.
Use risk management to improve the solution.

## Slide 8: Decision to Develop a Proposal
Development is costly and time consuming
Contractors must be realistic about their probability of winning a contract
Evaluate bid/no-bid decision
Many non-winning proposals hurt reputation
May be hard to decide to no-bid an RFP
Notes: Contractors interested in submitting a proposal must be realistic about the probability of being selected as the winning contractor.
Evaluating whether or not to go forward with the preparation of a proposal is sometimes referred to as the bid/no-bid decision.
Contractors need to be realistic about their ability to prepare proposals and about the probability of winning the contract because submitting a lot of non-winning proposals in response to RFPs can hurt a contractor’s reputation.

## Slide 9: Bid or No-Bid?
Factors to consider
  Competition
  Risk
  Mission
  Extension of capabilities
  Reputation
  Customer funds
  Proposal resources
  Project resources
Notes: Bid or No-Bid?
Some factors that a contractor might consider in making a bid/no-bid decision are:
Competition—which other contractors might also submit a proposal?
Risk—is there a risk that the project will be unsuccessful (either technically or financially)?
Mission—is the proposed project consistent with the contractor’s business mission?
Extension of capabilities—would the proposed project provide the contractor with an opportunity to extend and enhance its capabilities?
Reputation—what is the contractor’s reputation with the customer?
Customer funds—does the customer really have funds available to go forward with the project?
Proposal resources—are appropriate resources available to prepare a quality proposal?
Project resources—are appropriate resources available to perform the project if the contractor is selected as the winner?
  If a contractor is not sure that it has the resources to perform the project, it needs a plan for securing the necessary resources to successfully perform the project.

## Slide 10: Key Parts of a Proposal
Three sections
  Technical
  Management
  Cost
Detail level
  Depends on complexity of the project
  Requirements from the RFP

## Slide 11: Technical Section
The objective of this section is to convince the customer that the contractor understands the problem or need and can provide the least risky and most beneficial solution. The technical section should contain the following elements
Understand the need
Proposed approach or solution
Benefits to the customer
Notes: Understanding of the need—the contractor must show the customer that they thoroughly understand the problem to be solved.
Proposed approach or solution—the proposal should describe the approach or methodology that would be used in developing the solution.
Benefits to the customer—the contractor should state how the proposed solution or approach would benefit the customer and achieve the project’s success criteria or expected outcomes, including cost savings; reduced processing time; reduced inventory; better customer service; reduced errors; improved safety conditions; more timely information; reduced maintenance, etc.

## Slide 12: Management Section
Description of work tasks
Deliverables
Project schedule
Project organization
Related experience
Equipment and facilities

## Slide 13: Cost Section
Tangible Benefits
Intangible Benefits
Required Resources
Financial Return
Notes: Tangible Benefits- Tangible bene ﬁts are measurable and will corre­spond to the problem/opportunity described. For each bene ﬁ t, describe it and quantify it, including a translation of the bene ﬁ t into ﬁnancial terms such as dollars saved or gained. This is the place to establish the bene ﬁt-realization metrics that will be monitored after implementation.
Intangible Benefits-Intangible bene ﬁts are difﬁcult to measure, but are still important. For example, reducing complexity in a task may increase employee job satisfaction, a worthwhile bene ﬁ t but a difﬁcult one to measure.
Required resource (cost)- What labour and other resources will be required? Include a comment about the accuracy of these ﬁgures. Typical cost categories include internal (employee) labour hours, external labour, and capital investment.
Financial Return- There are many ﬁnancial methods that compare the tangible up-front cost of the project with the expected tangible bene ﬁts achieved over time.

## Slide 14: Typical costs
Include estimated costs
  Labor
  Materials
  Equipment
  Facilities
  Subcontractors and consultants
  Travel
  Documentation
  Overhead
  Escalation
  Contingency
  Fee or profit

## Slide 15: Pricing Considerations
Competition
Price
  Not overpriced or underpriced
Factors
  Reliability of cost estimates
  Risk
  Value of project to the contractor
  Customer’s budget
  Competition level

## Slide 16: Proposal Preparation
Proposal team
  Can be one person or many
  Various skills and expertise
  Proposal manager for large proposals
Proposal development
  Time for writing, review, and management approval
  Length dependent upon the RFP requirements
  Cost of proposal development is part of normal business costs
Notes:   In large scale efforts, the contractor may designate a proposal manager who coordinates the efforts.
  The proposal schedule must allow adequate time for writing, review, and approval by the management of the contractor’s organization.
  Proposals in response to RFPs can be as brief as a few pages or as long as hundreds of pages, including text and drawings.
  Customers do not pay contractors to prepare proposals. Contractors absorb the costs of proposal development as part of normal marketing costs.

## Slide 17: Brief Project proposal structure
Write executive summary
Project Background
Present your solution
Define project deliverables
List Resources required
State your conclusion

## Slide 18: Proposal Submission and Follow-up
Submission
On time
Formatted properly
Sent in manner required
  Hard copies
  E-mail
  Electronic form
Two sets by different delivery methods
Follow-up
Be proactive
Professional manner
Follow RFP guidelines
Notes: Proposal Submission and Follow-up
Proposals should be:
Submitted on time
  Late or incomplete proposals are often not accepted
Formatted properly
In the manner specified
Possibly deliver two sets by different delivery methods
  Depending on the dollar value of the proposal, some contractors have been known to hand-deliver the proposal or send two sets of proposals by different express mail services.
Contractors must continue to be proactive even after the proposal is submitted.
Any follow-up needs to be done in a professional manner and in accordance with the RFP guidelines.

## Slide 19
Differentiate a Request for Proposal (RFP) and a proposal document. Your answer should show differences in purpose, authorship content and initiator.
ⓘ Start presenting to display the poll results on this slide.
Discussion

## Slide 20: Contracting
It’s unwise to pay too much, but it’s worse to pay too little. When you pay too much, you lose a little money – that’s all. The contract document is important in all projects.
.
Notes:   Just because the contractor has been selected as the winner does not mean the contractor begins the work right away. Before the project can proceed, a contract must be signed between the customer and the contractor.
  The contract must clearly spell out the deliverables the contractor is expected to provide.
  It’s unwise to pay too much, but it’s worse to pay too little. When you pay too much, you lose a little money – that’s all. The contract document is important in all projects.

## Slide 21: Contracting Considerations
A contract is a vehicle for establishing good customer-contractor communications and arriving at a mutual understanding and clear expectations to ensure project success.
It is an agreement between the contractor, who consents to provide a product or service (deliverables), and the customer, who agrees to pay the contractor a certain amount in return.
Contract must be signed before starting work .
Notes:   Just because the contractor has been selected as the winner does not mean the contractor begins the work right away. Before the project can proceed, a contract must be signed between the customer and the contractor.
  The contract must clearly spell out the deliverables the contractor is expected to provide.
  It’s unwise to pay too much, but it’s worse to pay too little. When you pay too much, you lose a little money – that’s all. The contract document is important in all projects.

## Slide 22: Types of Contracts
Fixed Price- The total cost of the project is predetermined and agreed upon in advance.
  Cost-Reimbursement - The contractor reimburses the seller for the actual costs incurred during the project, plus an additional amount as profit or fee.
  Time and Material Contract - the buyer pays the seller for the actual time and materials used, plus an additional amount for profit.
  Fixed-Price Incentive Fee (FPIF) Contract - A fixed price contract with an additional incentive fee for meeting or exceeding predetermined performance criteria

## Slide 23: The Four ‘R’ of contractual relations

## Slide 24: Contract Terms and Conditions
Misrepresentation of costs
Notice of cost overruns or schedule delays
Approval of subcontractor
Customer furnished equipment of information
Patents
Disclosure of proprietary information
International considerations
Termination
Terms of payments
Bonus/penalty payments
Changes
Notes: Contract Terms and Conditions
The following are some of the terms and conditions that are commonly included in project contracts:
Misrepresentation of costs—states that it is illegal for the contractor to overstate the hours or costs expended on the project
Notice of cost overruns or schedule delays—outlines the circumstances under which the contractor must notify the customer of any schedule delays
Approval of subcontractor—indicates when the contractor needs to obtain approval before hiring a subcontractor
Customer-furnished equipment or information—lists the items that the customer will provide to the contractor throughout the project and the dates by which the customer will make these items available
Patents—covers ownership of patents that may result from conducting the project
Disclosure of proprietary information—prohibits one party from disclosing confidential information, technologies, or processes pertaining to the project
International considerations—specifies accommodations that must be made for customers from other countries
Termination—states the conditions under which the customer can terminate the contract, such as nonperformance by the contractor
Terms of payment—addresses the basis on which the customer will make payments to the contractor
Bonus/penalty payments—some contracts have a bonus provision, wherein the customer will pay the contractor a bonus if the project is completed ahead of schedule or exceeds other customer performance requirements
  On the other hand, some contracts include a penalty provision, wherein the customer can reduce the final payment to the contractor if the project is not completed on schedule or if performance requirements are not met.
Changes—Covers the procedure for proposing, approving, and implementing changes to the project scope or schedule

## Slide 25
List the key factors to developing a winning proposal.
ⓘ Start presenting to display the poll results on this slide.
Writing a Winning Proposal

## Slide 26: Measuring Proposal Success
Contractors measure the success of their proposal efforts by the number of times their proposals are selected by customers or by the total dollar value of their proposals that are selected.
Measures
Win ratio
  Number won/number submitted
  All proposals weighted equally
Total dollar value
  Value won/value submitted
  More weight to larger values
Strategies
Submit many to win fair share
  Increase chances of winning
  May be viewed negatively
Bid on potential successes
  Respond where better than average chance to win
  Must have bid/no-bid process
Notes: Some contractors have a strategy of submitting proposals in response to as many RFPs as they can with the hope that they will eventually win their fair share. Their philosophy is that if they do not submit a proposal then they do not have any chance to win and by submitting more proposals they increase their chances of winning more contracts.
Other contractors are more selective in submitting proposals; they respond to only those RFPs where they think they have a better-than-average chance of winning the contract. These contractors seriously consider the bid/no-bid decision process in responding to RFPs and submit fewer proposals in an attempt to have a high win ratio.

## Slide 27: Summary

## Slide 28: Key takeaway points
Project
Project proposal
Key parts of a proposal document
Contracting Strategy Considerations

## Slide 29: Next Lesson
Project Estimation

## Slide 30: References
Guide, P.M.B.O.K., (2017). A Guide to the Project Management Body of Knowledge (PMBOK® Guide), Project Management Institute.
Verzuh, E., 2015. The fast forward MBA in project management. John Wiley & Sons.
Ward, G.G., 2018. Effective project management: guidance and checklists for engineering and construction. John Wiley & Sons.
Thompson, I., Cox, A. and Anderson, L., 1998. Contracting strategies for the project environment. European Journal of Purchasing & Supply Management, 4(1), pp.31-41.