## Action Plan Template
Project Name: SAMPLE PROJECT 1
Goal: Build a website for your company
Action Step #1: Market research |  |  |  |  | Timeline |  |  | Resources
Priority | Task (Action Item) | Phase | Assigned | Status | Start Date | Due Date | Planned Hours | Department | Materials Required | Cost | Notes
High | Hire Marketing specialist | Planning | Sam H. | 50% |  |  | 3 weeks | HR |  | $
High | Gather data | Planning | Sam H. | 50% |  |  | 1 week | Marketing |  | $
Medium | Market segmentation | Planning | Ada L. | 75% |  |  | 1 week | Marketing |  | $
Low | Buyer personas brainstorm | Planning | John G., Helena H., Fred P. | 25% |  |  | 1 week | Marketing |  | $
Action Step #2: Design site |  |  |  |  | Timeline |  |  | Resources
Priority | Task (Action Item) | Phase | Assigned | Status | Start Date | Due Date | Planned Hours | Department | Materials Required | Cost | Notes
High | Create site architecture | Planning | Sam H. | 50% |  |  | 2 weeks | Web Development |  | $
High | Design the site's UI | Planning | Sam H. | 50% |  |  | 2 weeks | Web Development |  | $
Medium | Draft content | Planning | Ada L. | 75% |  |  | 1 week | Marketing |  | $
Low | Create images | Planning | John G., Helena H., Fred P. | 25% |  |  | 1 week | Marketing |  | $
Action Step #3: Launch site |  |  |  |  | Timeline |  |  | Resources
Priority | Task (Action Item) | Phase | Assigned | Status | Start Date | Due Date | Planned Hours | Department | Materials Required | Cost | Notes
High | Test site | Execution | Sam H. | 50% |  |  | 1 week | Web Development |  | $
Medium | SEO Work | Execution | Ada L. | 75% |  |  | 2 weeks | Marketing |  | $
Low | Create new pages | Execution | John G., Helena H., Fred P. | 25% |  |  | 2 weeks | Marketing |  | $
Low | Monitor site's health | Execution | John G., Helena H., Fred P. | 25% |  |  | 2 weeks | Marketing/Web Development |  | $
Free related templates
Gantt chart template for Excel
Project dashboard template for Excel
Project budget template for Excel

## How to Use This Template
Introduction
When you’re making a project, you start with a strategy. The action plan is that document. It outlines all the steps you need to do in order to accomplish your goal. This action plan template from ProjectManager.com has everything you need to start your project off right.
Definition of Terms
Priority: Notes whether the action is high, medium or low concern.
Task: A small action, one of the steps towards meeting a project goal.
Phase: Where you are in the overall course of the project life cycle.
Assigned: Has the task been assigned to a team member? Who?
Status: What is the percentage done?
Start Date: When tast should initiate.
Due Date: When the task must be complete.
Planned Hours: How long the task should take to get done.
Department: Which department is responsible for the task?
Materials Required: The material resources needed for the task.
Cost: Money allowed for task in budget.
Notes: Comments that don’t fall under other categories.