## Project Planner
Project Planner for Human Resources Management System
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS (DAYS)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Activity 01 | 1 | 5 | 1 | 4 | 25%
Activity 02 | 1 | 6 | 1 | 6 | 80% | bar: PERIODS (DAYS) 7
Activity 03 | 2 | 4 | 2 | 5 | 35%
Activity 04 | 4 | 8 | 4 | 6 | 10%
Activity 05 | 4 | 2 | 4 | 8 | 85%
Activity 06 | 4 | 3 | 4 | 6 | 85%
Activity 07 | 5 | 4 | 5 | 3 | 50%
Activity 08 | 5 | 2 | 5 | 5 | 60%
Activity 09 | 5 | 2 | 5 | 6 | 75%
Activity 10 | 6 | 5 | 6 | 7 | 100%
Activity 11 | 6 | 1 | 5 | 8 | 60%
Activity 12 | 9 | 3 | 9 | 3 | 0%
Activity 13 | 9 | 6 | 9 | 7 | 50%
Activity 14 | 9 | 3 | 9 | 1 | 0%
Activity 15 | 9 | 4 | 8 | 5 | 1%
Activity 16 | 10 | 5 | 10 | 3 | 80%
Activity 17 | 11 | 2 | 11 | 5 | 0%
Activity 18 | 12 | 6 | 12 | 7 | 0%
Activity 19 | 12 | 1 | 12 | 5 | 0%
Activity 20 | 14 | 5 | 14 | 6 | 0%
Activity 21 | 14 | 8 | 14 | 2 | 44%
Activity 22 | 14 | 7 | 14 | 3 | 0%
Activity 23 | 15 | 4 | 15 | 8 | 12%
Activity 24 | 15 | 5 | 15 | 3 | 5%
Activity 25 | 15 | 8 | 15 | 5 | 0%
Activity 26 | 16 | 28 | 16 | 30 | 50%