## Sheet1
Human Resources Management System Project Gantt Chart S275931
Project Phase | Task Name | Start Date | End Date | Assigned | Progress | 01.03.24 | 02.03.24 | 03.03.24 | 04.03.24 | 05.03.24 | 06.03.24 | 07.03.24 | 08.03.24 | 09.03.24 | 10.03.24 | 11.03.24 | 12.03.24 | 13.03.24 | 14.03.24 | 15.03.24 | 16.03.24 | 17.03.24 | 18.03.24 | 19.03.24 | 20.03.24 | 21.03.24 | 22.03.24 | 23.03.24 | 24.03.24 | 25.03.24 | 26.03.24 | 27.03.24 | 28.03.24 | 29.03.24 | 30.03.24 | 31.03.24 | 01.04.24 | Colour Legend
Initiation | Write Project Charter | 01.03.24 | 01.03.24 | Project Manager, Steering Committee, Project Sponsor | [34 empty] | Weekend
Initiation | Feasibility Study | 01.03.24 | 01.03.24 | Steering Committee, Project Sponsor | [34 empty] | Planned Timeline
Initiation | Define Scope | 01.03.24 | 01.03.24 | Steering Committee | [34 empty] | Actual Timeline
Initiation | Kick-off Meeting | 01.03.24 | 01.03.24 | Project Manager, Steering Committee, Project Sponsor
Planning | Create Project Management Plan | 04.03.24 | 05.03.24 | Project Manager
Panning | Create Financial Plan | 04.03.24 | 05.03.24 | Project Sponsor, Steering Committee
Planning | Create Resource Plan | 04.03.24 | 05.03.24 | Project Manager, Steering Committee
Planning | Create Quality Plan | 04.03.24 | 05.03.24 | Project Manager
Planning | Conduct Risk Assessment | 04.03.24 | 05.03.24 | Project Manager
Planning | Create Risk Management Plan | 04.03.24 | 05.03.24 | Project Manager
Planning | Create Acceptance Plan | 04.03.24 | 05.03.24 | Project Manager
Planning | Create Procurement Plan | 04.03.24 | 05.03.24 | Project Manager
Execution | Cast Project Vision and Team Leadership | 06.03.24 | 06.03.24 | Project Manager, Project Sponsor, Tech Leads, Team Leaders
Execution | Create Tasks | 06.03.24 | 06.03.24 | Project Manager, Team Leaders, Tech Leads
Execution | Brief team members on their tasks | 06.03.24 | 06.03.24 | Project Manager, Team Leaders, Tech Leads
Execution | Plan and design software | 07.03.24 | 08.03.24 | Software Designers, Software Engineers, UI/UX Designers
Execution | Develop, Code and Debug software | 11.03.03 | 22.03.24 | Frontend and Backend Programmers, Software Engineers, Database Developers, DevOps Engineers, Cybersecurity Specialists
Execution | Build Software | 13.03.24 | 22.03.24 | DevOps Engineers, Frontend and Backend Programmers, Software Engineers
Execution | Test Software | 13.03.25 | 22.03.24 | Testers, Cybersecurity Specialists, Software Engineers, DevOps Engineers
Execution | Deploy and Release Software | 25.03.24 | 25.03.24 | DevOps Engineers, Software Engineers
Execution | Receive Client Feedback | 06.03.24 | 25.03.24 | Project Manager, Team Leaders, Tech Leads, Steering Committee
Execution | Quality Assurance for Deliverables | 25.03.24 | 25.03.24 | Project Manager, Testers, Tech Leads, Team Leaders, Software and DevOps Engineers, Steering Committee
Execution | Communicate with team members and stakeholders | 06.03.24 | 25.03.24 | Project Manager, Team Leaders, Tech Leads, Steering Committee, Project Sponsor
Monitoring and Control | Risk Management | 26.03.24 | 29.03.24 | Project Manager, Tech Leads, Project Sponsor
Monitoring and Control | Acceptance Management | 26.03.25 | 29.03.25 | Project Manager, Steering Committee
Monitoring and Control | Cost Management | 26.03.26 | 29.03.26 | Project Manager, Project Administrators
Monitoring and Control | Quality Assurance | 26.03.27 | 29.03.27 | Project Manager, Testers, Tech Leads, Team Leaders, Software and DevOps Engineers, Steering Committee
Monitoring and Control | Change Management | 26.03.28 | 29.03.28 | Steering Committee, Project Sponsor
Monitoring and Control | Repeat planning, execution and monitoring phases if necessary (agile lifecycle) | Optional | Optional | All Team Members
Closure | Project Performance Analysis | 01.04.24 | 01.04.24 | Project Sponsor, Project Administrators, Project Manager, Steering Committee
Closure | Team Analysis | 01.04.24 | 01.04.24 | Project Manager, Tech Leads, Team Leaders, Project Administrators
Closure | Project Closure documentation, handover and signoff | 01.04.24 | 01.04.24 | Steering Committee, Project Sponsor, Project Manager, Project Administrators
Closure | Evaluation and Lessons Learnt | 01.04.24 | 01.04.24 | Project Sponsor, Project Manager, Project Administrators